## Worksheet
Event Planning Schedule Planner - Freelancer Style
Task | Date | Time Range | Assignee | Status | Priority
Finalize Event Concept & Theme | 2023-10-05 | 10:00 - 12:30 | Jane Doe | Pending | High
Secure Venue & Book Date | 2023-10-10 | 09:30 - 11:45 | Mike Johnson | Pending | High
Send Invitations to Guests | 2023-10-15 | 14:00 - 15:30 | Sarah Lee | Pending | Medium
Confirm Catering Menu & Services | 2023-10-18 | 13:00 - 15:00 | Jane Doe | Pending | High
Coordinate Audio/Visual Setup | 2023-10-20 | 11:00 - 13:30 | David Chen | Pending | Medium
Finalize Guest List & RSVP Tracking | 2023-10-22 | 10:30 - 12:00 | Sarah Lee | Pending | High
Conduct Full Rehearsal Session | 2023-10-25 | 14:00 - 17:30 | Mike Johnson | Pending | High
Finalize Event Run-Through Plan | 2023-10-27 | 09:30 - 11:45 | Jane Doe | Pending | Medium
Event Day - October 28, 2023
Setup & Venue Decoration | 2023-10-28 | 07:00 - 11:30 | All Team Members | Pending | High
Guest Arrival & Registration Check-in | 2023-10-28 | 13:00 - 14:00 | Sarah Lee, David Chen | Pending | High
Event Execution & Coordination | 2023-10-28 | 14:00 - 18:30 | Mike Johnson, Jane Doe | Pending | High
Post-Event Cleanup & Equipment Return | 2023-10-28 | 19:00 - 21:30 | All Team Members | Pending | Medium
Prepared by:Freelancer Event Planning Team ¦Last Updated:October 4, 2023