## Event Planning Schedule Planner
Event Planning Schedule Planner
Time | Activity/Task | Responsible Person(s) | Status | Notes/Remarks
8:00 AM - 9:00 AM | Morning Team Meeting | Project Manager, Coordinators | In Progress | Review event goals and assign tasks.
9:30 AM - 10:30 AM | Venue Selection & Site Visit | Event Coordinator, Logistics Team | Pending | Confirm availability and capacity.
11:00 AM - 12:30 PM | Catering Menu Finalization | Catering Manager, Chef | Pending | Send revised options for client approval.
1:00 PM - 2:30 PM | Speaker Confirmation & Briefing | Speaker Coordinator, AV Team | To Do | Email presentation requirements.
3:00 PM - 4:00 PM | Marketing & Social Media Plan Review | Marketing Lead, Designer | In Progress | Promotion calendar finalization.
Equipment & Logistics Checklist
— | Audio/Visual Setup (Projectors, Microphones) | AV Team | Not Started
— | Seating Arrangement & Signage Design | Design Team, Setup Crew | Pending
Final Pre-Event Tasks (1 Week Before)
Day 7: 9:00 AM | Final Walkthrough of Venue | Project Manager, Coordinators | In Progress
Day 5: 2:00 PM | Distribute Event Schedule to All Staff | HR & Admin Team | To Do | Email and printed copies.
Post-Event Follow-Up (Day After)
Next Day: 10:00 AM | Team Debrief Meeting | All Team Leaders | To Do | Capture lessons learned and feedback.
Day 2: 1:00 PM | Send Thank You Emails to Speakers & Vendors | Event Coordinator, Admin Team | To Do
© 2024 Event Planning Schedule Planner ¦ One-Page Template for Efficient Coordination