## Worksheet
Event Planning Schedule Planner
Small Business Edition - Monthly Overview
Task / Activity | Date & Time | Responsible Person | Status | Notes / Details
Finalize event theme and concept | 2024-04-05 ¦ 10:00 AM | Sarah Johnson | Pending | Submit mood board by EOD Friday.
Book venue and confirm availability | 2024-04-10 ¦ 2:30 PM | Marcus Lee | In Progress | Contacted 3 venues; awaiting quotes.
Send invites to 120 guests | 2024-04-15 ¦ 9:00 AM | Linda Chen | Pending | Email templates approved.
Confirm caterer and menu tasting | 2024-04-18 ¦ 1:00 PM | Sarah Johnson | In Progress | Tasting scheduled for April 17.
Arrange audio-visual setup and tech check | 2024-04-25 ¦ 3:00 PM | James Parker | Pending | Contact vendor for equipment list.
Final walkthrough and coordination meeting | 2024-04-30 ¦ 11:00 AM | All Team Members | Pending | Meeting scheduled at venue.