## Worksheet
Event Planning Schedule Planner - Team Use
Task/Activity | Responsible Team Member(s) | Start Date | End Date | Status | Priority
Define Event Objectives & Goals | Project Lead, Marketing Team | 2023-09-01 | 2023-09-05 | Pending | High
Secure Venue & Book Date | Logistics Team, Facilities Coordinator | 2023-09-06 | 2023-09-15 | In Progress | High
Develop Event Theme & Branding | Creative Team, Design Lead | 2023-09-10 | 2023-09-18 | In Progress | Medium
Create Guest List & Send Invitations | Events Coordinator, HR Team | 2023-09-16 | 2023-09-30 | Pending | High
Coordinate Catering & Food Services | Catering Manager, Logistics Team | 2023-09-18 | 2023-10-10 | Pending | Medium
Arrange Audiovisual & Stage Setup | Tech Team, AV Specialist | 2023-09-20 | 2023-10-15 | Pending | High
Confirm Speakers & Schedule Sessions | Program Director, Planning Committee | 2023-09-25 | 2023-10-18 | Pending | High
Finalize Event Schedule & Distribute to Team | Project Lead, All Teams | 2023-10-16 | 2023-10-25 | Pending | High
Conduct Final Walkthrough & Dry Run | Event Manager, All Team Leads | 2023-10-30 | 2023-11-05 | Pending | High
Post-Event Feedback Collection & Report | Project Lead, HR & Analytics Team | 2023-11-06 | 2023-11-15 | Pending | Medium
Last updated: October 2, 2023 ¦ Version: 1.1