## Worksheet
Event Planning Schedule Planner - Tracking View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Priority | Budget Allocated ($)
EP-001 | Finalize Event Concept & Theme | Jane Smith | 2024-06-15 | 2024-06-18 | Completed | High | 5,000.00
EP-002 | Book Venue & Confirm Availability | Michael Brown | 2024-06-19 | 2024-06-25 | In Progress | High | 15,000.00
EP-003 | Hire Catering & Menu Approval | Sarah Johnson | 2024-06-25 | 2024-07-15 | Pending | Medium | 8,500.00
EP-004 | Secure Entertainment & Performers | Daniel Lee | 2024-06-18 | 2024-07-15 | Pending | High | 7,200.00
EP-005 | Distribute Invitations & RSVP Tracking | Lisa Wang | 2024-07-16 | 2024-08-15 | Pending | Medium | 3,800.00
EP-006 | Campaign & Social Media Promotion Launch | Ryan Taylor | 2024-07-15 | 2024-08-31 | Pending | High | 6,900.00
EP-007 | Final Event Run-Through & Rehearsal | Amanda Clark | 2024-10-15 | 2024-10-25 | Pending | High | 4,300.00
EP-015 | Cleanup & Post-Event Report Submission | Taylor White | 2024-10-30 | 2024-11-15 | Pending | Low3,500.00
Total Budget Allocated: | [6 empty] | $69,200.00
This schedule planner is designed for tracking event planning tasks with real-time status updates, resource allocation, and timeline monitoring.