## Worksheet
Event Planning Task Manager - Business Use
Task ID | Task Name | Description | Assigned To | Due Date | Prioritization | Status
T001 | Finalize Event Concept & Theme | Define core theme, target audience, and event objectives. | Sarah Johnson | 2024-04-15 | High | In Progress
T002 | Select Venue & Confirm Booking | Visit potential venues, negotiate terms, and finalize contract. | Michael Chen | 2024-04-18 | High | Pending
T003 | Develop Budget Proposal | Outline estimated costs and allocate funds per category. | Laura Thompson | 2024-04-16 | Medium | In Progress
T004 | Secure Vendor Contracts (Catering, AV, Decor) | Contact and sign agreements with key vendors. | David Kim | 2024-04-25 | High | Pending
T005 | Create Invitation & RSVP System | Design digital invites and set up tracking tool. | Emily Rodriguez | 2024-04-20 | Medium | Completed
T006 | Coordinate Marketing Campaigns | Launch email, social media, and press outreach. | Nina Patel | 2024-04-30 | Medium | Pending
T007 | Conduct Staff & Volunteer Briefing | Organize training session for event team. | Sarah Johnson | 2024-05-10 | Low | Pending
T008 | Final Run-through & Setup Check | Verify all logistics and conduct dry run day before. | Michael Chen | 2024-05-15 | High | Pending
© 2024 Business Event Planning Team ¦ This is a sample task manager template for business use.