## Worksheet
Event Planning Task Manager
Task ID | Task Description | Assigned To | Due Date | Status | Priority
#T001 | Finalize event venue booking | Jane Smith | 2024-06-15 | In Progress | High
#T002 | Send invitations to guests | Mike Johnson | 2024-06-18 | Pending | Medium
#T003 | Book catering services | Lisa Chen | 2024-06-12 | Completed | High
#T004 | Arrange audiovisual setup | David Kim | 2024-06-16 | In Progress | Medium
#T005 | Confirm speaker lineup | Sarah Williams | 2024-06-14 | Pending | High
#T006 | Design event banners & signage | Alex Rivera | 2024-06-17 | Pending | Medium
#T007 | Finalize event schedule | Emma Davis | 2024-06-13 | In Progress | High
#T008 | Coordinate transportation for guests | Tom Brown | 2024-06-19 | Pending | Low
#T009 | Prepare event registration system | Laura Green | 2024-06-11 | Completed | Medium
#T010 | Conduct final walkthrough of venue | Jane Smith | 2024-06-20 | Pending | High
Tasks Total
10In Progress
3Completed