## Event Planning Task Manager
Event Planning Task Manager
Task ID | Task Name | Description | Assigned To | Due Date | Priority | StatusProgress (%) (Optional)
TP-001 | Finalize Event Theme & Concept | Select overarching theme, color palette, and branding elements for the event. | Jane Smith | 2024-05-15 | High | In Progress
TP-002 | Secure Venue Booking | Negotiate and sign contract with selected event venue. | Mark Johnson | 2024-05-18 | High | In Progress
TP-003 | Send Invitations to Guests | Distribute digital and physical invitations with RSVP details. | Sarah Lee | 2024-05-22 | Medium | In Progress
TP-004 | Coordinate Catering Menu & Dietary Needs | Confirm food options, allergies, and special meal requests with vendor. | David Kim | 2024-05-25 | Medium | Delayed
TP-005 | Arrange Audiovisual Equipment & Tech Support | Book projectors, microphones, and ensure tech team is on-site. | Lisa Tran | 2024-05-30 | Low | In Progress
TP-006 | Conduct Final Walkthrough of Venue | Review layout, seating, signage, and all setup elements one week prior. | Alex Brown | 2024-06-15 | High | Completed