## Worksheet
Task ID | Task Description | Assigned To | Due Date | Budgeted Cost ($) | Actual Cost ($) | Status
T001 | Finalize Venue Contract | Jane Smith | 2023-10-15 | 5,000.00 | 4,850.75 | Pending
T002 | Book Catering Services | Mike Johnson | 2023-10-18 | 7,500.00 | 7,345.25 | Pending
T003 | Design Invitations & Branding Materials | Sarah Lee | 2023-10-10 | 2,500.00 | 2,475.89 | Completed
T004 | Hire Audio/Visual Team | David Kim | 2023-10-12 | 4,800.00 | 4,955.42 | Overdue
T005 | Secure Entertainment Act (Band) | Lisa Chen | 2023-10-25 | 6,200.00 | 5,987.56 | Pending
T006 | Arrange Transportation for VIP Guests | Tom Wilson | 2023-11-05 | 3,800.00 | 3,674.32 | Pending
T007 | Confirm Speaker Agendas & Presentations | Anna Brown | 2023-10-14 | 1,800.00 | 1,765.44 | Completed
T008 | Finalize Event Timeline & Schedule | Ryan Patel | 2023-11-01 | 950 | 876.45 | Pending
Total Budgeted Cost:$32,550.00
Total Actual Cost:$31,926.68