## Worksheet
Event Planning Task Manager - Multi Page Template
Task ID | Task Description | Assigned To | Due Date | Status
TASK-001 | Define event purpose and goals | Project Manager | 2023-11-05 | In Progress
TASK-002 | Select event date and venue | Event Coordinator | 2023-11-15 | Pending
TASK-003 | Create preliminary budget estimate | Finance Lead | 2023-11-10 | Pending
TASK-004 | Develop initial guest list (target: 250) | Marketing Lead | 2023-11-20 | Pending
TASK-005 | Identify key stakeholders and sponsors | Sponsorship Manager | 2023-11-12 | Pending
Task ID | Task Description | Assigned To | Due Date | Status
TASK-006 | Finalize venue contract and deposits | Event Coordinator | 2023-11-30 | Pending
TASK-007 | Arrange catering and menu options | Catering Manager | 2023-12-15 | Pending
TASK-008 | Book audiovisual equipment and technicians | Technical Lead | 2023-12-10 | Pending
TASK-009 | Develop event program and schedule | Event Coordinator | 2023-12-18 | Pending
TASK-010 | Arrange transportation and parking options | Logistics Lead | 2023-12-5 | Pending
Task ID | Task Description | Assigned To | Due Date | Status
TASK-011 | Create event marketing materials (digital and print) | Marketing Lead | 2023-12-25 | Pending
TASK-012 | Launch email invitations and registration portal | Marketing Lead | 2023-12-30 | Pending
TASK-013 | Confirm all vendor contracts and deposits | Event Coordinator | 2024-01-05 | Pending
TASK-014 | Conduct final walkthrough and site inspection | Event Manager | 2024-01-15 | Pending
TASK-015 | Finalize team assignments and run-through schedule | Project Manager | 2024-01-20 | Pending