## Worksheet
Task | Due Date | Status | Assigned To | Priority | Notes
Pick Event Venue | 2023-10-15 | Not Started | Jane Doe | High | Consider indoor and outdoor options.
Create Guest List | 2023-10-18 | In Progress | John Smith | Medium | Include family, friends, and colleagues.
Send Invitations | 2023-10-25 | Not Started | Jane Doe | High | Email and physical invites required.
Arrange Catering | 2023-10-20 | In Progress | Mike Johnson | High | Confirm dietary restrictions.
Select Theme and Decorations | 2023-10-17 | In Progress | Sarah Lee | Medium | Theme: Garden Party.
Hire Entertainment | 2023-10-22 | Not Started | David Brown | Medium | Band or DJ needed.
Plan Schedule & Agenda | 2023-10-24 | In Progress | Jane Doe | High | Include speeches, activities, and breaks.
Confirm Logistics (Transportation, Parking) | 2023-10-19 | Not Started | John Smith | Medium | Contact shuttle service.
Finalize Budget & Expense Tracking | 2023-10-26 | In Progress | Sarah Lee | High | Track all receipts and invoices.
Conduct Final Walkthrough | 2023-10-30 | Not Started | All Team Members | High | Schedule time before event day.