## Worksheet
Event Planning Task Manager
Printable Version - Track all tasks for successful event execution
# | Task Description | Category | Assigned To | Due Date | Status
1 | Finalize event theme and concept | Planning | Jane Doe | 2023-10-15 | Pending
2 | Book venue and confirm availability | Logistics | John Smith | 2023-10-10 | Pending
3 | Create guest list and send invitations | Communication | Sarah Lee | 2023-10-12 | Completed
4 | Arrange catering and menu selection | Food & Beverage | Mike Johnson | 2023-10-18 | In Progress
5 | Coordinate audiovisual equipment and tech setup | Technical | Lisa Wong | 2023-10-16 | Pending
6 | Confirm speaker or entertainment bookings | Program & Talent | Tony Reed | 2023-10-14 | In Progress
7 | Develop event schedule and timeline | Scheduling | Jane Doe | 2023-10-13 | Completed
8 | Create event signage and directional materials | Design & Print | Sarah Lee | 2023-10-17 | Pending
Total Tasks: |  |  |  |  | 8