## Worksheet
Event Planning Task Manager - Report Version
Task ID | Task Description | Assigned To | Due Date | Status | Prioritization
#TP001 | Finalize event venue booking and contract signing | Emily Chen | 2023-11-05 | Completed | High
#TP002 | Design and distribute event invitation templates | Jacob Miller | 2023-11-10 | In Progress | High
#TP003 | Confirm catering menu and dietary accommodations | Sophia Lee | 2023-11-15 | Pending | Medium
#TP004 | Secure audio-visual equipment and technical support | David Kim | 2023-11-18 | Pending | High
#TP005 | Coordinate with keynote speaker and schedule rehearsals | Laura Thompson | 2023-11-20 | Pending | Medium
#TP006 | Send out reminders to confirmed attendees | Nina Patel | 2023-11-25 | Pending | Low
#TP007 | Prepare on-site registration and check-in system | James Wilson | 2023-11-30 | Pending | Medium
Report generated onOctober 18, 2023¦ Event Name: Annual Tech Summit