## Worksheet
Event Planning - Time Tracker (Analysis View)
Task | Start Date | End Date | Planned Duration (hrs) | Actual Duration (hrs) | Variance (hrs) | Status | Budgeted Cost ($) | Actual Cost ($) | Variance ($)
Concept Development | 2023-10-01 | 2023-10-05 | 48 | 54 | 6 | Pending Review | 3,200.00 | 3,780.00 | 580
Vendor Selection & Contracts | 2023-10-15 | 2023-10-31 | 96 | 84 | -12 | Closed | 7,500.00 | 7,250.00 | -250
Schedule & Logistics Coordination | 2023-11-01 | 2023-11-15 | 72 | 88 | 16 | In Progress | 5,400.00 | 6,320.00 | 920
Marketing & Promotion Campaign | 2023-11-16 | 2023-12-15 | 96 | 96 | -0.5 (estimate)
Total Hours: | [7 empty] | 312
TOTALS: |  |  | 240 | 322 | 82 |  | 16,100.00 | 17,359.99 | +1,259.99
Note:Data reflects real-time tracking for event planning activities. Variance values indicate deviation from planned estimates.