## Worksheet
Event Planning - Time Tracker Dashboard
Event Name: Annual Tech Conference 2024
Date: October 15-17, 2024Organizer: Sarah Johnson
Task | Assigned To | Start Date | End Date | Status | Hours Logged
Preliminary Planning & Budgeting | Marketing Team | 2024-06-01 | 2024-07-31 | Overdue | 85.5
Schedule Development & Finalization | Project Coordination Team | 2024-07-15 | 2024-09-15 | In Progress | 67.3
Speaker Recruitment & Confirmation | Outreach Coordinator | 2024-07-01 | 2024-08-31 | In Progress | 56.8
Registration Portal Setup & Testing | IT Department | 2024-08-15 | 2024-09-30 | On Track | 78.1
Venue Contract Negotiation & Signing | Procurement Team | 2024-06-15 | 2024-07-31 | Completed | 34.5
Logistics & Travel Coordination | Operations Manager | 2024-09-01 | 2024-10-15 | On Track | 63.7
Promotion & Social Media Campaigns | Marketing Team | 2024-08-01 | 2024-10-15 | In Progress | 96.3
Total Hours Logged: |  |  |  |  | 582.2