## Worksheet
Event Planning - Time Tracker (Planning View)
Task / Activity | Pre-Event Planning |  |  | Event Execution |  |  | Post-Event Wrap-Up
| Week 1 (Planning) | Week 2 (Coordination) | Week 3 (Finalization) | Day of Event | Morning | Afternoon | Day After | 1 Week Later | 2 Weeks Later
Venue Booking & Contracting | Schedule site visit Due: 2023-10-15 | Secure final agreement Due: 2023-10-29 | Sign contract & deposit Due: 2023-11-05 | Confirm setup Check-in: 8:00 AM | Setup team arrival 9:00 AM | Stage & audio check 11:30 AM | Clean venue After event | Send thank-you emails 2023-11-15 | Finalize budget report 2023-11-30
Guest List Management | Create initial list Due: 2023-10-15 | Send invites (email) Due: 2023-10-31 | Update RSVPs Due: 2023-11-05 | Confirm final count Due: 8:00 AM | Check-in station ready 9:30 AM | Handle late arrivals 11:45 AM | Collect feedback forms After event | Send follow-up survey 2023-11-18 | Analyze feedback data 2023-12-05
Catering & Logistics | Select catering vendor Due: 2023-10-18 | Confirm menu options Due: 2023-10-31 | Finalize food count & allergies Due: 2023-11-05 | Arrival of catering team 7:30 AM | Set up buffet stations 8:45 AM | Serve refreshments 10:00 AM - 2:30 PM | Collect leftover food After event | Settle vendor invoice 2023-11-25 | Review vendor performance 2023-12-07
Speaker Coordination & Agenda | Identify keynote speaker Due: 2023-10-10 | Confirm schedule & slides Due: 2023-10-28 | Finalize session times Due: 2023-11-04 | Brief speakers before start 8:50 AM | Host opening remarks 9:15 AM | Manage transitions & breaks 10:30 AM, 12:30 PM | Review session recordings After event | Share recording with guests 2023-11-28 | Archive digital assets 2023-12-15
Marketing & Promotion | Design social media graphics Due: 2023-10-15 | Launch email campaign Due: 2023-10-30 | Post final reminders Due: 2023-11-04 | Display event signage 7:45 AM | Live social media updates 9:00 AM - 3:00 PM | Post highlights after event 11:30 PM | Publish recap blog post 2023-11-25 | Share metrics report 2023-12-06 | Archive marketing content 2023-12-18