## Worksheet
Event Planning Time Tracker - Startup Style
Task Name | Start Date | End Date | Assigned To | Status | Estimated Hours | Actual Hours
Venue Booking & Negotiation | 2024-01-15 | 2024-01-30 | Jane Doe | In Progress | 8.5 | 6.75
Catering Coordination | 2024-01-16 | 2024-01-31 | John Smith | In Progress | 6 | 5.5
Speaker Confirmations & Travel Arrangements | 2024-01-17 | 2024-01-31 | Sarah Lee | Not Started | 7.5 | - - -
Marketing & Social Media Campaign Launch | 2024-01-20 | 2024-01-31 | Mike Johnson | In Progress | 9.5 | 7.85
Event Program Development & Review | 2024-01-21 | 2024-01-30 | Lisa Chen | In Progress | 5.5 | 4.75
Registration System Setup & Testing | 2024-01-23 | 2024-01-31 | Daniel Park | In Progress | 8 | 5.95
On-Site Logistics & Staff Coordination | 2024-01-25 | 2024-01-31 | Amy Roberts | In Progress | 7 | 6.85
Post-Event Follow-Up & Feedback Collection | 2024-02-15 | 2024-03-15 | Jane Doe | Not Started | 6.5 | - - -
Total Hours (Estimated) | [5 empty] | 68 | 47.65
Created using Startup-Style Time Tracker Template for Event Planning ¦ Version 1.0