## Worksheet
Advanced Event Planning To-Do List
Task ID | Task Description | Category | Due Date | Prioritization | Status
#001 | Finalize event venue contract and deposit payment | Logistics | 2024-05-30 | High | Completed
#002 | Design and send invitations (digital & physical) | Communication | 2024-06-15 | High | Completed
#003 | Confirm catering menu and dietary restrictions | Catering | 2024-06-18 | Medium | Completed
#004 | Arrange audiovisual equipment and test run | Technical Setup | 2024-06-25 | High | Pending
#005 | Confirm speaker schedule and travel arrangements | Program Coordination | 2024-06-12 | Medium | Pending
#006 | Develop event agenda and distribute to team | Planning & Organization | 2024-06-14 | Medium | Pending
#007 | Arrange signage and room setup diagrams | Visuals & Layout | 2024-06-24 | Low | Pending
#008 | Conduct final walkthrough of venue with vendor team | Logistics & Coordination | 2024-06-27 | High | Pending
#009 | Prepare emergency response plan and first aid kits | Safety & Compliance | 2024-06-15 | Medium | Pending
#010 | Send follow-up emails to attendees with event details | Communication | 2024-06-28 | Low | Pending