## Worksheet
Event Planning To-Do List - Business Use
Task ID | Task Description | Responsible Person | Due Date | Status
T001 | Define event objectives and goals | Marketing Director | 2024-05-31 | Pending
T002 | Secure venue and confirm availability | Event Coordinator | 2024-06-15 | In Progress
T003 | Develop event budget and cost estimates | Finance Manager | 2024-06-10 | In Progress
T004 | Finalize guest list and send invitations | HR Manager | 2024-06-25 | Pending
T005 | Arrange catering and refreshments | Catering Manager | 2024-07-10 | Pending
T006 | Book audiovisual equipment and technical support | IT Specialist | 2024-07-15 | Pending
T007 | Confirm speaker and session schedule | Event Coordinator | 2024-06-30 | In Progress
T008 | Design and print promotional materials | Graphic Designer | 2024-07-12 | Pending
T009 | Conduct final walkthrough and setup rehearsal | Event Manager | 2024-07-25 | Pending
T010 | Post-event evaluation and feedback collection | Project Lead | 2024-08-05 | Pending