## Worksheet
Event Planning To-Do List - Client View
Task | Due Date | Status | Priority | Assigned To
Finalize guest list and send invites | 2025-04-10 | Pending | High | Marketing Team
Book venue and confirm availability | 2025-03-15 | In Progress | High | Event Coordinator
Arrange catering and menu tasting | 2025-03-25 | Pending | High | Catering Manager
Confirm entertainment and schedule setup | 2025-04-01 | Pending | Medium | Entertainment Lead
Design and print event invitations | 2025-03-18 | Completed | Medium | Graphic Designer
Coordinate with vendors for delivery schedule | 2025-04-05 | Pending | High | Venue Manager
Prepare event agenda and speaker notes | 2025-04-08 | In Progress | High | Event Planner
Conduct final walkthrough and setup check | 2025-04-13 | Pending | High | Safety & Logistics Team