## Event Planning To-Do List
Task ID | Task Description | Assigned To | Due Date | Priority | Status | Budget (USD)
EVT-001 | Secure venue reservation and confirm contract details | Jane Smith | 2024-05-15 | High | In Progress | $8,500.00
EVT-002 | Finalize event theme, decor, and color scheme | Mike Johnson | 2024-05-18 | High | In Progress | $3,200.00
EVT-003 | Send out invitations and RSVP tracking setup | Sarah Lee | 2024-05-12 | Medium | In Progress | $1,800.00
EVT-004 | Book caterer and finalize menu with tasting session | David Brown | 2024-05-16 | Medium | In Progress | $6,750.00
EVT-005 | Arrange transportation and shuttle services for guests | Lisa Garcia | 2024-05-21 | Low | Completed | $950.00
EVT-006 | Hire and schedule entertainment (band/dj) for evening event | Robert Taylor | 2024-05-19 | Medium | In Progress | $4,300.00
EVT-007 | Create detailed timeline and run-of-show for event day | Jane Smith | 2024-05-25 | High | In Progress | $1,200.00
EVT-008 | Coordinate photo/video team and post-event content plan | Sarah Lee | 2024-05-30 | Low | In Progress | $2,500.00
EVT-009 | Finalize vendor agreements and sign all contracts | David Brown | 2024-05-17 | Medium | Completed | $1,000.00
EVT-010 | Conduct full event walkthrough and logistics check with team | Mike Johnson | 2024-05-31 | High | In Progress | $750.00
Total Estimated Cost: | [5 empty] | $37,150.00