## Worksheet
Event Planning To-Do List
Task | Date Due | Priority | Status | Assigned To
Finalize event concept and theme | 2023-06-15 | High |  | Jane Doe
Book venue and confirm availability | 2023-06-18 | High |  | John Smith
Send invitations to guests | 2023-06-20 | Medium |  | Sarah Wilson
Arrange catering and menu approval | 2023-06-25 | High |  | Mike Johnson
Coordinate with vendors (decor, music, lighting) | 2023-06-27 | Medium |  | Lisa Brown
Plan event schedule and timeline | 2023-07-01 | High |  | Jane Doe
Conduct final walkthrough and site prep | 2023-07-05 | High |  | John Smith
Prepare emergency kit and on-site contact list | 2023-07-06 | Medium |  | Sarah Wilson
Collect feedback forms and thank-you notes | 2023-07-10 | Low |  | Lisa Brown
Finalize post-event report and budget summary | 2023-07-15 | Medium |  | Mike Johnson
Update client portfolio with event highlights | 2023-07-20 | Low |  | Jane Doe
Archive all event files and materials | 2023-07-30 | Low |  | John Smith
Follow-up with key vendors for feedback | 2023-08-05 | Medium |  | Sarah Wilson
Review and adjust event planning checklist for next project | 2023-08-10 | Medium |  | Lisa Brown
Host team debrief meeting and celebrate success | 2023-08-15 | High |  | Mike Johnson