## Worksheet
Event Planning - Manager View To-Do List
Task ID | Task Description | Assigned To | Deadline | Priority | Status
EVT-001 | Finalize event venue contract and deposit payment | John Smith | 2024-04-15 | High | In Progress
EVT-002 | Confirm keynote speaker and send contract | Sarah Johnson | 2024-04-18 | High | Pending
EVT-003 | Create event marketing materials (flyers, email templates) | Mike Davis | 2024-04-21 | Medium | Pending
EVT-004 | Coordinate catering menu tasting and finalize order | Lisa Brown | 2024-04-16 | Medium | In Progress
EVT-005 | Update event registration system with new pricing tiers | Alex Turner | 2024-04-19 | Low | Pending
EVT-006 | Organize on-site event staff schedules and training session | Jennifer Lee | 2024-04-17 | Medium | Pending
EVT-007 | Review and approve final event timeline with all stakeholders | David Wilson | 2024-04-25 | High | Pending
EVT-008 | Collect and organize attendee feedback forms post-event | Rachel Green | 2024-05-15 | Low | Pending
Summary:Total Tasks: 8 ¦ Completed: 0 ¦ In Progress: 2 ¦ Pending: 6
Last Updated: April 5, 2024