## Worksheet
Event Planning To-Do List - Planning View
Task | Due Date | Priority | Status | Assigned To | Notes / Details
Purchase event venue deposit | 2024-04-15 | High | Pending | John Doe | Confirm availability for 80 guests, 3 weeks in advance.
Finalize guest list & send invites | 2024-04-25 | High | In Progress | Jane Smith | Include RSVP tracking via online form.
Book caterer & menu tasting | 2024-05-01 | High | Pending | Alex Johnson | Include dietary options: vegetarian, vegan, gluten-free.
Arrange entertainment & schedule | 2024-05-10 | Medium | Pending | Sarah Lee | Live band with 3-hour set including opening and closing acts.
Design & print invitations | 2024-04-18 | Medium | Pending | Marcus Brown | Coordinate with designer; proofread before printing.
Plan event layout & seating chart | 2024-05-15 | Medium | Pending | Linda Chen | Include VIP section and accessibility needs.
Confirm vendor contracts & deposits | 2024-05-20 | High | Pending | John Doe | Send signed contracts via email & retain digital copies.
Conduct final walkthrough of venue | 2024-05-30 | Medium | Pending | Jane Smith | Check lighting, audio, setup layout, and emergency exits.
Prepare event day timeline & checklist | 2024-06-01 | High | Pending | All Team Members | Distribute to all coordinators and vendors.
Coordinate with security & transportation | 2024-06-03 | Medium | Pending | Sarah Lee | Arrange shuttle service for guests from parking.