## Event Planning To-Do List
Event Planning To-Do List
Task ID | Task Description | Assigned To | Due Date | Status | Prioritization(1-5)(High=5)
ETL-001 | Define event objective and scope | Jane Smith | 2024-04-15 | Pending | 5
ETL-002 | Select venue and confirm availability | Michael Brown | 2024-04-18 | In Progress | 5
ETL-003 | Develop event budget and secure funding | Sarah Johnson | 2024-04-16 | Pending | 5
ETL-004 | Create guest list and send invitations | Daniel Lee | 2024-04-17 | In Progress | 4
ETL-005 | Arrange catering and menu selection | Lisa Wong | 2024-04-19 | Pending | 5
ETL-006 | Schedule entertainment and speakers | Robert Garcia | 2024-04-18 | Pending | 5
ETL-007 | Design and print event materials (banners, flyers) | Elena Martinez | 2024-04-16 | Completed | 3
ETL-008 | Coordinate logistics and transportation plan | Alex Turner | 2024-04-17 | In Progress | 4
ETL-009 | Conduct final walkthrough and site inspection | Jane Smith | 2024-04-25 | Pending | 5
ETL-010 | Finalize event program and schedule | Sarah Johnson | 2024-04-23 | Pending | 5
Legend: