## Worksheet
Event Planning To-Do List
Summary View - Track Key Tasks and Progress
Task | Responsible | Due Date | Status | Priority
Purchase event venue | John Doe | 2023-10-15 | In Progress | High
Book catering services | Jane Smith | 2023-10-18 | Pending | High
Design event invitations | Sarah Lee | 2023-10-10 | Completed | Medium
Finalize guest list | Michael Brown | 2023-10-12 | In Progress | High
Arrange transportation for guests | Amy Wilson | 2023-10-20 | Pending | Medium
Confirm audio/visual equipment | David Kim | 2023-10-17 | In Progress | High
Plan event schedule and agenda | Jessica Taylor | 2023-10-14 | Completed | High
Arrange decorations and themes | Lisa Garcia | 2023-10-19 | Pending | Medium
Total Tasks: 8 | Completed: 2 ¦ In Progress: 3 ¦ Pending: 3