## Worksheet
Event Planning - To-Do List (Tracking View)
Task ID | Task Description | Assigned To | Due Date | Status | Priority | Progress (%)
T001 | Define event theme and concept | Jane Doe | 2023-10-15 | Pending | High | 0%
T002 | Book venue and confirm availability | John Smith | 2023-10-20 | In Progress | High | 65%
T003 | Create guest list and send invitations | Sarah Lee | 2023-10-25 | Pending | Medium | 10%
T004 | Finalize catering menu and confirm orders | Mike Johnson | 2023-11-05 | Pending | High | 0%
T005 | Arrange audiovisual equipment and setup | Lisa Brown | 2023-11-10 | Pending | Medium | 5%
T006 | Coordinate with performers or speakers | Alex Taylor | 2023-11-15 | Pending | High | 0%
T007 | Set up event registration system | Jane Doe | 2023-11-20 | In Progress | High | 40%
T008 | Create event timeline and schedule of activities | John Smith | 2023-11-25 | Pending | Medium | 0%
T009 | Conduct final walkthrough and site inspection | Sarah Lee | 2023-12-01 | Pending | High | 0%
T010 | Prepare emergency and contingency plans | Mike Johnson | 2023-12-05 | Pending | Medium | 0%