## Weekly Budget - Manager View
WEEKLY BUDGET REPORT - EVENT PLANNING (MANAGER VIEW)
Week Ending | Event Name | Category | Budgeted ($) | Actual ($) | Variance ($) | Status
2024-04-05 | Spring Launch Event | Marketing & Promotion | 5,000.00 | 4,785.63 | 214.37 | On Track
2024-04-05 | Corporate Gala 2024 | Venue & Catering | 15,000.00 | 14,875.32 | 124.68 | On Track
2024-04-05 | Tech Conference Workshop | Speaker & Training | 8,500.00 | 9,132.56 | -632.56 | Over Budget
2024-04-05 | Team Building Retreat | Travel & Accommodation | 12,000.00 | 11,895.78 | 104.22 | On Track
2024-04-05 | Product Launch Party | Entertainment & Decor | 6,300.00 | 6,891.23 | -591.23 | Over Budget
2024-04-05 | Customer Appreciation Day | Gifts & Supplies | 3,500.00 | 3,187.45 | 312.55 | On Track
TOTALS: |  |  | 49,300.00 | 46,778.97 | +2,521.03 | Overall: On Track
Notes & Recommendations:
- Speaker & Training costs exceeded budget due to last-minute guest speaker. Consider booking confirmed speakers earlier. - Entertainment & Decor overspent slightly; review vendor quotes for next event. - Overall weekly spending is under target, with positive variance of $2,521.03.