## Worksheet
Weekly Budget Report - Event Planning
Category | Planned Budget ($) | Actual Spend ($) | Variance ($) | Status
Marketing & Promotion | 15,000.00 | 13,250.75 | +1,749.25 | Under Budget
Event Venue & Rentals | 35,000.00 | 36,245.90 | -1,245.90 | Over Budget
Catering & Refreshments | 20,000.00 | 19,453.67 | 546.33 | Under Budget
Audiovisual Equipment | 12,000.00 | 12,876.45 | -876.45 | Over Budget
Speaker Fees & Travel | 25,000.00 | 23,142.89 | +1,857.11 | Under Budget
Staffing & Labor | 18,000.00 | 17,925.33 | 74.67 | Under Budget
Total | 125,000.00 | 123,894.99 | +1,105.01 | Under Budget Overall
Notes:The weekly budget report shows a positive variance of $1,105.01 overall, indicating efficient spending across most categories. The venue and AV rentals exceeded the planned budget slightly; these items should be reviewed for cost optimization in upcoming weeks.
Last Updated: June 9, 2024 ¦ Prepared By: Finance & Events Team