## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status | Progress (%)
Budget Forecasting | 2024-03-15 | 2024-03-25 | 10 | Finance Team | Completed | 100
Revenue Stream Analysis | 2024-03-26 | 2024-04-10 | 15 | Business Analysts | In Progress | 65
Expense Tracking Setup | 2024-04-11 | 2024-04-30 | 20 | Accounting Officer | Not Started | 0
Monthly Financial Review | 2024-05-01 | 2024-05-31 | 30 | Finance Manager | Planned | 0
Cash Flow Projection | 2024-06-01 | 2024-06-30 | 30 | Financial Modeling Team | Not Started | 0
Financial Management – Client View Gantt Chart (Version 1.0)