## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status | Progress (%)
Budget Planning | 2024-03-01 | 2024-03-15 | 15 | Finance Team | Completed | 100
Revenue Forecasting | 2024-03-16 | 2024-04-10 | 35 | Analytics Team | In Progress | 65
Expense Tracking Setup | 2024-04-11 | 2024-05-30 | 60 | IT & Admin | Not Started | 0
Cash Flow Analysis | 2024-05-31 | 2024-06-25 | 35 | Finance Manager | Not Started | 0
Monthly Review & Adjustment | 2024-06-26 | 2024-07-31 | 35 | Executive Team | Not Started | 0