## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Budget Allocation ($) | Status | Progress (%) | Dependencies
FIN-001 | Initial Financial Planning & Forecasting | 2024-03-15 | 2024-03-31 | 17 | Sarah Johnson | 50,000.00 | Completed | 100% | None
FIN-002 | Revenue Stream Analysis & Modeling | 2024-04-01 | 2024-05-15 | 65 | James Reed | 75,000.00 | In Progress | 68% | FIN-001
FIN-003 | Expense Budget Review & Adjustment | 2024-04-10 | 2024-05-20 | 51 | Linda Chen | 60,000.00 | Pending Start | 0% | FIN-002
FIN-004 | Monthly Cash Flow Projections (Q2) | 2024-05-01 | 2024-06-30 | 60 | Michael Torres | 45,000.00 | Not Started | 0% | FIN-003
FIN-005 | Financial Risk Assessment & Mitigation Plan | 2024-06-01 | 2024-07-15 | 55 | Emily Wright | 80,000.00 | Planned | 0% | FIN-004
FIN-006 | Annual Financial Review & Reporting | 2024-08-15 | 2024-09-30 | 46 | Daniel Kim | 95,000.00 | Not Started | 0% | FIN-005