## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Status | Progress (%)
Budget Planning & Forecasting | 2024-01-01 | 2024-01-31 | 30 | Finance Director | Completed | 100
Cash Flow Analysis | 2024-02-01 | 2024-02-15 | 15 | Finance Analyst | In Progress | 75
Expense Review & Control | 2024-02-16 | 2024-03-31 | 57 | Accounting Manager | Not Started | 0
Monthly Financial Reporting | 2024-04-01 | 2024-04-30 | 30 | Finance Team | Not Started | 0
Audit Preparation & Compliance Check | 2024-05-01 | 2024-05-31 | 31 | Internal Auditor | Not Started | 0