## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Budget Forecasting | 2024-03-01 | 2024-03-15 | 15 | Sarah Chen | On Track
Revenue Analysis | 2024-03-16 | 2024-04-05 | 21 | James Reed | In Progress
Expense Tracking Setup | 2024-04-06 | 2024-04-20 | 15 | Lisa Patel | Not Started
Monthly Financial Review | 2024-04-21 | 2024-05-10 | 21 | Team Finance | Planned
Cash Flow Projection | 2024-05-11 | 2024-05-31 | 21 | David Kim | Pending Approval