## Worksheet
Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status
Budget Planning & Forecasting | 2024-03-01 | 2024-03-15 | 15 | Sarah Johnson | On Track
Cash Flow Analysis | 2024-03-16 | 2024-03-31 | 16 | Michael Chen | In Progress
Expense Review & Categorization | 2024-04-01 | 2024-04-15 | 15 | Emily Rodriguez | Not Started
Revenue Projection & Modeling | 2024-04-16 | 2024-05-10 | 35 | David Kim | Planned
Financial Reporting Cycle Setup | 2024-05-11 | 2024-05-31 | 31 | Lisa Thompson | On Track
Audit Preparation & Compliance Check | 2024-06-01 | 2024-06-30 | 30 | James Wilson | Not Started