## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Manager | Status | Progress (%)
Budget Planning & Forecasting | 2024-01-15 | 2024-01-30 | 15 | Sarah Johnson | On Track | 95%
Revenue Stream Analysis | 2024-02-01 | 2024-02-15 | 15 | Michael Chen | In Progress | 60%
Expense Review & Optimization | 2024-02-16 | 2024-03-15 | 30 | Emily Davis | Not Started | 0%
Cash Flow Projection | 2024-03-16 | 2024-04-10 | 25 | David Lee | On Track | 85%
Financial Reporting & Compliance | 2024-04-11 | 2024-05-31 | 60 | Lisa Wong | Planned | 10%