## Worksheet
Task ID | Task Name | Start Date | End Date th> | Status | Responsible Person | Budget (USD)
FM-001 | Annual Budget Planning | 2024-03-01 | 2024-03-31 | In Progress | Jane Doe | 50,000.00
FM-002 | Quarterly Financial Review2024-06-152024-06-30Pending | John Smith | 15,000.00
FM-003 | Expense Analysis & Reporting | 2024-04-15 | 2024-05-31 | Completed | Lisa Brown | 35,000.00
FM-004 | Purchase Order Approval Flow Setup | 2024-07-15 | 2024-11-30 | Not Started | Mike Johnson | 8,500.00
FM-005 | Fiscal Year Projection Model Build | 2024-12-15 | 2025-03-31 | Not Started | Sarah Lee | 67,000.00
Project Summary (Page 2)
This multi-page Gantt chart outlines key financial management tasks across fiscal quarters. Each task includes start/end dates, assigned responsibility, and budget allocation. Progress status is updated monthly for tracking.
Notes
- All dates are in YYYY-MM-DD format. - Budget figures are in USD. - Status updates must be reviewed quarterly by Finance Director.
Timeline Overview (Gantt View)
FM-001 | Annual Budget Planning | Mar 2024 |  |  | Jane Doe | 50,000.00
FM-002 | Quarterly Review | Jun 2024 |  |  | Pending | 15,000.00
FM-003 | Expense Analysis | Apr–May 2024 |  |  | Lisa Brown | 35,000.00
FM-004 | Purchase Flow Setup | Jul 2024 – Nov 2024 |  |  | Mike Johnson | 8,500.00
FM-005 | Fiscal Projection Model | Dec 2024 – Mar 2025 |  |  | Sarah Lee | 67,000.00