## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Financial Planning & Forecasting | 2024-03-01 | 2024-03-15 | 15 | Finance Lead | In Progress
Budget Approval Process | 2024-03-16 | 2024-03-31 | 16 | Finance Manager | Planned
Expense Tracking Setup | 2024-04-01 | 2024-04-10 | 10 | Accountant | Scheduled
Revenue Stream Analysis | 2024-04-11 | 2024-05-05 | 35 | Business Analyst | Not Started
Monthly Financial Report Automation | 2024-05-06 | 2024-06-30 | 65 | IT & Finance Team | Not Started