## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status | Milestones
Budget Planning & Forecasting | 2024-03-01 | 2024-03-15 | 15 | Finance Team | On Track | Initial Budget Approved
Expense Tracking Setup | 2024-03-16 | 2024-04-05 | 21 | Operations Team | In Progress | System Integration Complete
Monthly Financial Review Meetings | 2024-04-06 | 2024-12-31 | 369 | Finance & Strategy Team | Planned | Quarterly Reports Due
Cash Flow Forecasting | 2024-05-01 | 2024-06-30 | 61 | Finance Team | On Track | Forecast Verified by CFO
Reconciliation & Audit Preparation | 2024-07-01 | 2024-08-15 | 56 | Accounting Team | Pending | Audit Checklist Finalized