## Worksheet
Date | Maintenance Task | Description | Responsible Person | Estimated Cost (USD) | Actual Cost (USD) | Status | Budget Category | Approval Required? | Notes
2024-03-15 | Server Hardware Upgrade | Replace aging server rack with high-density model for improved performance and scalability. | Jane Smith | 12,500.00 | 12,300.00 | Completed | IT Infrastructure | No | Equipment was delivered and installed within schedule.
2024-04-10 | Fiscal Year Audit Preparation | Review all financial transactions for accuracy and compliance with accounting standards. | Mark Johnson | 8,000.00 | 8,000.00 | In Progress | Financial Compliance | Yes | Preliminary review completed; awaiting final audit report.
2024-05-03 | Software Licensing Renewal | Renew licenses for enterprise resource planning (ERP) software to maintain operational continuity. | Alicia Brown | 6,200.00 | 6,200.00 | Completed | Software & Licensing | No | All licenses updated successfully.
2024-06-18 | Cash Flow Review & Forecasting | Analyze historical cash flows to develop a 9-month financial forecast for the next fiscal year. | David Lee | 3,500.00 | 3,450.00 | Completed | Financial Planning | No | Predictive model validated with past performance data.