## Worksheet
Date | Maintenance Task | Responsible Team Member | Estimated Cost (USD) | Actual Cost (USD) | Status | Notes
2024-03-15 | Server Backup Verification | John Doe | 150 | 150 | Completed | All backups verified and stored in secure cloud.
2024-03-20 | Network Cable Inspection | Sarah Lee | 75 | 75 | Completed | No damage found; all cables properly labeled.
2024-03-25 | Software Update Deployment | Michael Chen | 200 | 195 | Completed | All systems updated successfully with minimal downtime.
2024-04-01 | Firewall Configuration Review | Lisa Wu | 300 | 325 | In Progress | Reviewing access logs; pending final approval.
2024-04-05 | Security Audit Preparation | Team Lead - Finance & IT | 450 | 450 | Completed | Audit checklist finalized and shared with stakeholders.