## Worksheet
Project Name | Budget (USD) | Start Date | End Date | Status | Actual Spend (USD) | Variance (%) | Responsible Team | Financial Review Date
Digital Transformation Initiative | 500,000 | 2024-01-15 | 2024-12-31 | On Track | 425,000 | -15.0% | IT & Strategy Team | 2024-10-10
Customer Experience Upgrade | 300,000 | 2024-03-01 | 2024-11-30 | On Track | 285,000 | -5.0% | Marketing & Operations | 2024-10-15
Cloud Migration Project | 750,000 | 2024-02-10 | 2024-12-31 | At Risk | 680,000 | -9.3% | IT Infrastructure Team | 2024-10-25
Supply Chain Optimization | 450,000 | 2024-05-15 | 2024-11-30 | Pending Approval | 0 | - | Operations & Finance | 2024-10-30