## Worksheet
Task | Responsible | Start Date | End Date | Budget (USD) | Status | Notes
Project Initiation | Project Manager | 2024-01-15 | 2024-01-31 | 5,000 | Completed
Requirements Gathering | Business Analyst | 2024-02-01 | 2024-02-15 | 8,000 | In Progress | Finalize user needs and scope.
Design Phase | UX Designer | 2024-03-01 | 2024-03-31 | 12,000 | Pending | Finalize wireframes and UI.
Development | Software Team | 2024-04-01 | 2024-06-30 | 50,000 | Not Started | Build core application modules.
Testing & Quality Assurance | QA Team | 2024-07-01 | 2024-07-31 | 15,000 | Not Started | Execute functional and regression tests.
Deployment | IT Operations | 2024-08-01 | 2024-08-15 | 5,000 | Not Started | Launch to production environment.
Post-Implementation Review | Project Manager | 2024-09-01 | 2024-09-15 | 3,000 | Not Started | Evaluate performance and user feedback.