## Worksheet
Task | Owner | Start Date | End Date | Budget (USD) | Status | Progress (%)
Project Initiation & Planning | Alex Morgan | 2024-03-15 | 2024-03-25 | 5,000 | Completed | 100%
Market Research & Analysis | Jamie Lee | 2024-03-26 | 2024-04-10 | 8,500 | In Progress | 65%
Financial Modeling & Forecasting | Taylor Reed | 2024-04-11 | 2024-04-30 | 12,000 | Not Started | 0%
Budget Approval & Allocation | Sam Carter | 2024-05-01 | 2024-05-15 | 3,800 | Not Started | 0%
Resource Allocation & Team Setup | Jordan Wu | 2024-05-16 | 2024-05-31 | 4,200 | In Progress | 40%
Financial Management – Project Plan (Freelancer Style)