## Worksheet
Task | Responsible Party | Start Date | End Date | Budget Allocation (USD) | Status | Progress (%) | Remarks
Project Initiation & Feasibility Study | Financial Manager | 2024-03-01 | 2024-03-15 | $15,000 | Completed | 100% | Approved by Board of Directors.
Budget Finalization & Approval Process | Finance Director | <2024-03-162024-04-10 | $50,000 | In Progress | 75% | Waiting for vendor quotes.
Resource Allocation & Staffing Plan | HR & Project Lead | 2024-04-11 | 2024-05-30 | $35,000 | Pending Approval | 20% | Final staffing model under review.
Financial Risk Assessment & Mitigation Plan | Internal Auditor | 2024-05-01 | 2024-05-31 | $10,000 | Not Started | - | Initial risk matrix to be developed.
Quarterly Financial Review & Reporting | Finance Team | 2024-06-01 | 2024-12-31 | $45,000 (Annual) | Planned | - | Monthly reports will be submitted to management.