## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Budget Allocation (USD) | Status | Key Deliverables
Feasibility Analysis | 2024-03-01 | 2024-03-31 | Finance & Strategy | 50,000 | Completed | Market assessment report, ROI projections
Project Planning | 2024-04-01 | 2024-04-30 | Project Management Office | 75,000 | In Progress | Detailed project schedule, risk assessment plan
Resource Allocation | 2024-05-01 | 2024-05-31 | HR & Operations | 60,000 | Pending Approval | Team structure, budget distribution sheet
Execution Phase | 2024-06-01 | 2024-09-30 | Operations & Finance | 450,000 | Not Started | Monthly financial reports, milestone reviews
Review & Adjustment | 2024-10-01 | 2024-10-31 | Audit & Compliance | 30,000 | Planned | Financial audit report, variance analysis