## Worksheet
Project Phase | Start Date | End Date | Responsible Team | Budget Allocation (USD) | Status | Key Deliverables
Feasibility Study | 01/03/2024 | 05/03/2024 | Finance & Strategy | $50,000 | On Track | Market analysis report, cost-benefit model
Project Planning | 06/03/2024 | 15/04/2024 | Project Management Office | $75,000 | In Progress | Detailed project plan, risk assessment document
Execution Phase | 16/04/2024 | 30/06/2024 | Operations & Finance Teams | $300,000 | Pending Start | Monthly financial reports, milestone reviews
Review & Optimization | 01/07/2024 | 30/08/2024 | Finance & Audit Department | $40,000 | Not Started | Financial performance review, process improvements
Post-Implementation Audit | 01/09/2024 | 30/09/2024 | Internal Audit Team | $35,000 | Planned | Final audit report, compliance check