## Worksheet
Task | Start Date | End Date | Status | Responsible | Budget (USD)
Project Initiation | 2024-01-01 | 2024-01-15 | Completed | John Smith | 5,000.00
Feasibility Study | 2024-01-16 | 2024-02-14 | In Progress | Sarah Lee | 8,500.00
Requirements Gathering | 2024-02-15 | 2024-03-31 | Pending | Michael Chen | 12,000.00
Design Phase | 2024-04-01 | 2024-05-31 | Not Started | Lisa Wong | 15,000.00
Development Phase | 2024-06-01 | 2024-11-30 | Not Started | David Kim | 75,000.00
Testing & Quality Assurance | 2024-12-01 | 2025-01-31 | Not Started | Nina Patel | 18,000.00
Deployment & Go-Live | 2025-02-01 | 2025-02-15 | Not Started | James Taylor | 10,000.00