## Worksheet
Project Phase | Start Date | End Date | Responsible Party | Budget Allocation (USD) | Actual Spend (USD) | Status | Key Deliverables | Risk Assessment | Dependencies
Feasibility Study | 2024-03-01 | 2024-03-15 | Finance Department | 50,000 | 48,250 | Completed | Market analysis report, ROI projection | Low - market stability confirmed | External consultant engagement
Project Planning & Budget Finalization | 2024-03-16 | 2024-04-10 | Project Management Office (PMO) | 150,000 | 147,800 | On Track | Detailed project plan, Gantt chart, risk register | Medium - vendor lead times uncertain | Feasibility study approval, procurement planning
Design & Development Phase | 2024-04-11 | 2024-07-30 | Engineering & IT Team | 750,000 | 695,400 | On Schedule | System architecture, prototype demo, UI/UX mockups | High - integration with legacy systems | Stakeholder review of design, API access approved
Testing & Quality Assurance | 2024-08-01 | 2024-09-15 | QA Department | 120,000 | 118,600 | Completed | Bug log report, test coverage summary | Low - minor bugs resolved post-release | Development phase completion, access to staging environment
Deployment & Go-Live | 2024-09-16 | 2024-10-10 | IT Operations & Support | 85,000 | 84,350 | Completed | Live system rollout, user training materials | Medium - initial user feedback loop ongoing | QA sign-off, final data migration completed
Post-Implementation Review & Optimization | 2024-10-11 | 2024-11-30 | Finance & Operations Leadership | 60,000 | 59,750 | In Progress | Performance metrics report, cost-saving recommendations | Low - minor process improvements identified | Deployment success, user adoption data available