## Worksheet
Project Name | Start Date | End Date | Budget (USD) | Allocated Funds | Status | Responsible Person | Key Milestones | Financial Review Date | Notes
Digital Transformation Initiative | 2024-03-01 | 2025-06-30 | 500,000.00 | 325,478.50 | On Track | Sarah Thompson | Phase 1 Launch (Apr 2024), System Integration (Sep 2024) | 2024-09-15 | No budget overruns; system performance above target.
Revenue Growth Campaign | 2024-04-10 | 2024-10-31 | 350,000.00 | 289,654.30 | Completed | Michael Reynolds | Marketing Launch (May 2024), ROI Analysis (Aug 2024) | 2024-09-30 | Achieved 15% revenue uplift; campaign exceeded KPIs.
Cost Optimization Project | 2024-05-01 | 2024-11-30 | 400,000.00 | 367,892.50 | In Progress | Lisa Chen | Vendor Review (Jun 2024), Process Audit (Jul 2024) | 2024-08-15 | Preliminary savings estimated at $75,000.
Customer Experience Upgrade | 2024-06-15 | 2025-03-31 | 600,000.00 | 455,238.75 | Planning Phase | David Kim | User Research (Jul 2024), Design Approval (Oct 2024) | 2024-10-31 | Initial user feedback indicates strong engagement potential.